## Sheet1
PF200 Timeline
* Indicates this task can be the starting point for this milestone
Start Date | Completed Date | Due Date | Time Actual (hrs) | Time Req (hrs) | Dependent On | ID | Sub-ID#s |  | Milestone | Task | SubTask 1 | SubTask 2 | SubTask 3 | Deliverables
[5 empty] | * | MM |  |  | Monroe Meeting |  |  |  |  | Meeting with faculty advisor on project
2019-10-22 | 2019-10-22 | 2019-10-22 | 1 hour | 1 hour |  |  | 1 |  |  | Meeting with Monroe to review our priorities and gain insight on PF200 deisng |  |  |  | Advisor weighs in on task list and feasibility
[6 empty] | CPC |  |  | Create Project Concept |  |  |  |  | Documentation of system to be created
2019-10-22 |  | 2019-09-23 |  |  | *MM |  | 1 |  |  | Brainstorm Ideas |  |  |  | Whiteboard/sketch of system
2019-10-22 |  | 2019-09-23 |  |  | MM |  | 2 |  |  | Understand Flow through PF200 |  |  |  | Be able to present on flow through plant
2019-10-22 |  | 2019-09-23 |  |  | MM |  | 3 |  |  | Determine total flow rate through design |  |  |  | Set Q
2019-10-22 |  | 2019-09-23 |  |  | MM |  | 4 |  |  | Determine constants used in design moving forward |  |  |  | Determine SA of Sed talk, retention time in flocculator, baffle spacing, filter SA, filter height for backwash
2019-10-22 |  | 2019-09-23 |  |  | MM |  | 5 |  |  | Parameter definition based on constants |  |  |  | Outline design of all parameters
2019-10-22 |  | 2019-09-23 |  |  | MM |  | 6 |  |  | Create timeline of project |  |  |  | Plan for future points in project
[6 empty] | PD |  |  | Project Definition
2019-10-22 |  | 2019-09-26 |  |  | *CPC |  | 1 |  |  | Understand Customer requirements |  |  |  | Create a list of deliverables the customer wants from system
|  | 2019-09-26 |  |  | CPC.1 |  | 2 |  |  | Translate deliverables into engineering requirements |  |  |  | Transition from requirements into engineering inputs and constraints
|  | 2019-09-26 |  |  | CPC.2 |  | 3 |  |  | Determine more detailed parameters to be designed around to fit engineering requirements |  |  |  | Limitation of feasible solution and how to determine the best possible solution
|  | 2019-09-26 |  |  | CPC.3 |  | 4 |  |  | Review project definition with advisors from Aguaclara |  |  |  | Agreement on plan moving forward and how to implement system
[6 empty] | PS |  |  | Proposed Solution |  |  |  |  | All design parameters defined
[5 empty] | PD.2 |  | 1 |  |  | Determine architecture of solution
[5 empty] | PD.2 |  |  | 1 |  |  | Filter exit design finalized |  |  | Filter parameters finalized
[5 empty] | PD.2 |  |  | 2 |  |  | Sed tank bottom geometry finalized |  |  | Sed tank parameters finalized
[5 empty] | PD.2 |  |  | 3 |  |  | Flocculator design finalized |  |  | Flocculator parameters finalized
[7 empty] | 2 |  |  | Bill of materials created |  |  |  | Report and summary of coding done by system
[8 empty] | 1 |  |  | Stress tests on design of components
[8 empty] | 2 |  |  | Advisor Check
[8 empty] | 3 |  |  | Order materials from McMaster-Carr |  |  | Approval from advisor
[6 empty] | FC |  |  | Fabricate Components